## Sprint 11
Sprint 11 (10/19 - 10/30)
Product Development / Maintain update
Thời gian: 2026-10-19 → 2026-10-30 · Dữ liệu đánh giá (eval/)
STT | Nhóm trạng thái | Task | Loại | Task cha | App Name. | Trạng thái | Người làm | Ưu tiên | Hạn | Ước lượng (h) | Người tạo | Điểm | Git Pull Request | Ngày tạo | Mô tả
1 | ready to progress | 1.1.2 - Fix crash màn camera | Task |  | AR Dog | ready to progress | Bùi Văn Tiến |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-12 | Fix crash khi mở camera filter lần đầu trên Android 13. https://console.firebase.google.com/eval
2 | ready to progress | 1.0.7 - Add ads/Edit UI | Task |  | Speak2 | ready to progress | Nguyễn Nhật Minh |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-12 | Gắn 2 vị trí native, sửa UI màn home theo figma. - Link SRS https://docs.google.com/document/d/eval-speak2-107/edit - Link UI https://www.figma.com/design/eval-speak2-107/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-speak2-107-tracking/edit
3 | ready to progress | 1.1.3 - Add feature/Add ads | Task |  | PS Remote | ready to progress |  | urgent |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-13 | 1. Thêm tính năng điều khiển bằng giọng nói (bật/tắt, chuyển kênh). 2. Gắn inter khi kết nối thành công. - Link SRS https://docs.google.com/document/d/eval-psremote-113/edit - Link UI https://www.figma.com/design/eval-psremote-113/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-psremote-113-tracking/edit
4 | ready to progress | 1.1.3 - Add New feature mini game/Add ads | Task |  | AR Dog | ready to progress |  | high |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-13 | Mục tiêu: thêm mini game cho thú cưng trên màn camera AR (3 trò), bảng điểm, chia sẻ ảnh. Gắn ads theo file mới, tracking 10 event. - Link SRS https://docs.google.com/document/d/eval-ardog-113/edit - Link UI https://www.figma.com/design/eval-ardog-113/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-ardog-113-tracking/edit
5 | ready to progress | 1.1.4 - Fix ads/Fix luồng | Task |  | AR Dog | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-13 | Fix native too small màn kết quả, chuyển paywall sau onboarding. - Link SRS https://docs.google.com/document/d/eval-ardog-114/edit - Link UI https://www.figma.com/design/eval-ardog-114/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-ardog-114-tracking/edit
6 | ready to progress | 1.1.4 - Fix policy | Task |  | PS Remote | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-13 | Fix policy native too small theo template: https://docs.google.com/spreadsheets/d/eval-policy
7 | ready to progress | 1.0.8 - Add feature cloud save | Task |  | Game Emulator | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-14 | Đồng bộ save state lên Drive, chọn bản save khi mở game, màn quản lý bản save. - Link SRS https://docs.google.com/document/d/eval-emu-108/edit - Link UI https://www.figma.com/design/eval-emu-108/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-emu-108-tracking/edit
8 | ready to progress | 1.2.0 - Fix ads/Edit UI | Task |  | Spin wheel | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-14 | Fix ads theo file mới, edit UI màn quay và màn kết quả. - Link SRS https://docs.google.com/document/d/eval-spinwheel-120/edit - Link UI https://www.figma.com/design/eval-spinwheel-120/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-spinwheel-120-tracking/edit
9 | ready to progress | 1.1.2 - Add tracking/Fix luồng | Task |  | Auto click | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-15 | Thêm 8 event tracking, sửa luồng tạo kịch bản. - Link SRS https://docs.google.com/document/d/eval-autoclick-112/edit - Link UI https://www.figma.com/design/eval-autoclick-112/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-autoclick-112-tracking/edit
10 | ready to progress | 1.0.8 - Fix ads/Fix luồng | Task |  | Lovetest | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-15 | Fix ads màn kết quả, đổi luồng onboarding 2 màn. - Link SRS https://docs.google.com/document/d/eval-lovetest-108/edit - Link UI https://www.figma.com/design/eval-lovetest-108/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-lovetest-108-tracking/edit
11 | ready to progress | 1.1.8 - Fix IAP/Fix luồng | Task |  | VPN | ready to progress |  |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-16 | Fix restore purchase, bỏ màn intro thứ 2, cập nhật billing 7. - Link SRS https://docs.google.com/document/d/eval-vpn-118/edit - Link UI https://www.figma.com/design/eval-vpn-118/UI?node-id=1-2 - Tracking https://docs.google.com/spreadsheets/d/eval-vpn-118-tracking/edit
12 | ready to progress | 1.0.9 - Edit UI | Task |  | live video 2 | ready to progress |  | low |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-16 | Edit UI màn player trên tablet theo figma. https://www.figma.com/design/eval-lv2
Tổng (chỉ tính task gốc, tránh cộng trùng subtask)
Ghi chú: file sinh bởi eval/build_cases.py.

## Sprint 10
Sprint 10 (10/6 - 10/17)
Product Development / Maintain update
Thời gian: 2026-10-06 → 2026-10-17 · Dữ liệu đánh giá (eval/)
STT | Nhóm trạng thái | Task | Loại | Task cha | App Name. | Trạng thái | Người làm | Ưu tiên | Hạn | Ước lượng (h) | Người tạo | Điểm | Git Pull Request | Ngày tạo | Mô tả
1 | done | 1.0.2 - Add ads/Add SDK | Task |  | Phone Cleaner | done | Ngọc Văn Linh, Bùi Văn Tiến |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-05
2 | ready to release | 1.1.2 - Add feature/ Add ads | Task |  | PS Remote | ready to release | Nguyễn Nhật Minh |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-05
3 | done | Edit flow download/add flow auto scan game | Task |  | Game Emulator | done | Trần Đức An |  |  |  | BA Nguyễn Thị Hoa |  |  | 2026-10-05
Tổng (chỉ tính task gốc, tránh cộng trùng subtask)
Ghi chú: file sinh bởi eval/build_cases.py.